## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Hiba | 2026-02-21 | NumPy version conflict with TensorFlow | Sprint 1 | Hiba | Standards | Hardcoded the Tesseract executable path in the environment settings. | 2026-02-22 | Closed | fixed
2 | Hiba | 2026-03-07 | Excessive RAM usage when processing high-res PNG files | Sprint 2 | Hiba | Maintainability | Added a size check to downscale images before passing to the AI layer. | 2026-03-08 | closed | fixed
3 | Hiba | 2026-03-18 | Dashboard UI hangs when 'Verify' button is clicked multiple times | Sprint 3 | Hiba | User Interface | Integrated st.spinner and disabled the button during active processing. | 2026-03-19 | Closed | fixed
4 | Hiba | 30--April-2026 | Slow dashboard update after prediction | Sprint 4 | Hiba | User Interface | Optimized frontend rendering and reduced API calls | 2026-04-01 | Closed | fixed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others